## IM
Item | BQ Model & Dashboard Activities | Global or Environment Specific | Dependency | Environment |  |  | Owner | Comments
|  |  |  | Dev | QA | Prod
1 | Monitoring Project is created | Global |  | Completed | Completed | Completed | Platform Team
2 | Logging Sink Dataset is created in Monitoring Project | Global | Item 1 | Completed | Completed | Completed | Platform Team
3 | Create Broad Authorized Views for Airflow & BQ Logs on Monitoring Tables in auth_base_views dataset | Environment | Item 2 | Completed | Completed | Pending | Data Engineer / Product Owner | Advisable to create views through composer. Waiting for Production Deployment of Code.
4 | Create Domain Level Dataset in all environment | Environment |  | Completed | Completed | Completed | Platform Team
5 | Add necessary authorizations (4 Authorizations per environment for new domain and 1 Authorizations per environment for new lob but existing domain) | Environment | Items 2 & 4 | Completed | Completed | Completed | Product Owner | Need to request someone from Joe's team preferably Rod Miller
6 | Create Audit Control Views for new lob in LOB Level Dataset | Environment |  | Completed | Completed | Pending | Data Engineer | Waiting for Production Deployment of Code.
7 | Create Operations, Cost Consumption & Audit Control Views for new domain or update existing Audit Control View for just new lob in Domain Level Dataset | Environment | Items 3, 4 & 6 | Completed | Completed | Pending | Data Engineer | Waiting for Production Deployment of Code.
8 | Add Operations views in Consumer Project for new lob | Environment | Item 7 | Completed | Completed | Pending | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
9 | Update Cost Consumption & Audit Control Views for new domain | Environment | Item 7 | Completed | Completed | Pending | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
10 | Insert records in Domain LOB Source System Mapping Table in Consumer Project | Environment |  | Completed | Completed | Pending | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
11 | Change LookML Views to accommodate new LOB or new Domain Changes. | Environment | Items 8, 9 & 10 | Completed | Completed | Pending | Looker Developer | Waiting for Production Deployment of Code.

## PKU
Item | BQ Model & Dashboard Activities | Global or Environment Specific | Dependency | Environment |  |  | Owner | Comments
|  |  |  | Dev | QA | Prod
1 | Monitoring Project is created | Global |  |  |  |  | Platform Team
2 | Logging Sink Dataset is created in Monitoring Project | Global | Item 1 |  |  |  | Platform Team
3 | Create Broad Authorized Views for Airflow & BQ Logs on Monitoring Tables in auth_base_views dataset | Environment | Item 2 |  |  |  | Data Engineer / Product Owner | Advisable to create views through composer. Waiting for Production Deployment of Code.
4 | Create Domain Level Dataset in all environment | Environment |  |  |  |  | Platform Team
5 | Add necessary authorizations (4 Authorizations per environment for new domain and 1 Authorizations per environment for new lob but existing domain) | Environment | Items 2 & 4 |  |  |  | Product Owner | Need to request someone from Joe's team preferably Rod Miller
6 | Create Audit Control Views for new lob in LOB Level Dataset | Environment |  |  |  |  | Data Engineer | Waiting for Production Deployment of Code.
7 | Create Operations, Cost Consumption & Audit Control Views for new domain or update existing Audit Control View for just new lob in Domain Level Dataset | Environment | Items 3, 4 & 6 |  |  |  | Data Engineer | Waiting for Production Deployment of Code.
8 | Add Operations views in Consumer Project for new lob | Environment | Item 7 |  |  |  | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
9 | Update Cost Consumption & Audit Control Views for new domain | Environment | Item 7 |  |  |  | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
10 | Insert records in Domain LOB Source System Mapping Table in Consumer Project | Environment |  |  |  |  | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
11 | Change LookML Views to accommodate new LOB or new Domain Changes. | Environment | Items 8, 9 & 10 |  |  |  | Looker Developer | Waiting for Production Deployment of Code.

## BP
Item | BQ Model & Dashboard Activities | Global or Environment Specific | Dependency | Environment |  |  | Owner | Comments
|  |  |  | Dev | QA | Prod
1 | Monitoring Project is created | Global |  |  |  |  | Platform Team
2 | Logging Sink Dataset is created in Monitoring Project | Global | Item 1 |  |  |  | Platform Team
3 | Create Broad Authorized Views for Airflow & BQ Logs on Monitoring Tables in auth_base_views dataset | Environment | Item 2 |  |  |  | Data Engineer / Product Owner | Advisable to create views through composer. Waiting for Production Deployment of Code.
4 | Create Domain Level Dataset in all environment | Environment |  |  |  |  | Platform Team
5 | Add necessary authorizations (4 Authorizations per environment for new domain and 1 Authorizations per environment for new lob but existing domain) | Environment | Items 2 & 4 |  |  |  | Product Owner | Need to request someone from Joe's team preferably Rod Miller
6 | Create Audit Control Views for new lob in LOB Level Dataset | Environment |  |  |  |  | Data Engineer | Waiting for Production Deployment of Code.
7 | Create Operations, Cost Consumption & Audit Control Views for new domain or update existing Audit Control View for just new lob in Domain Level Dataset | Environment | Items 3, 4 & 6 |  |  |  | Data Engineer | Waiting for Production Deployment of Code.
8 | Add Operations views in Consumer Project for new lob | Environment | Item 7 |  |  |  | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
9 | Update Cost Consumption & Audit Control Views for new domain | Environment | Item 7 |  |  |  | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
10 | Insert records in Domain LOB Source System Mapping Table in Consumer Project | Environment |  |  |  |  | Data Engineer / Product Owner | For Production, Need to request someone from Joe's team preferably Rod Miller to execute the SQL Scripts.
11 | Change LookML Views to accommodate new LOB or new Domain Changes. | Environment | Items 8, 9 & 10 |  |  |  | Looker Developer | Waiting for Production Deployment of Code.