## TD2BQ Activities
Activity | SubActivity | Automation Tool / Service
BTEQ Conversion & DDL Generator | Generate Teradata View DDLs in sql files and generate list of all db objects | Custom Teradata view DDL SQL file generation Python utility
| Generate DDLs for Views using BigQuery Translation Service | BigQuery Translation Service
| Generate DDLs for Tables using DDL Converter | Custom BQ Table DDL Generator Teradata & Python Script
| Execute DAG that creates database objects (Tables / Views / Stored Procedure) | Create DB Objects DDL DAG
| Download all BTEQs from Unix Folders and Extract Teradata Stored Procedures Definitions | Custom Scripts Download Utility
| Convert all BTEQs and Stored Procedures using BQ Translation Service | Native BQ Translation Service
| Add Parameterization and other common changes using Bulk Edits \ Replacements | Custom Bulk Edit Routines
| Add Duplicate Checks Conditions for Core Tables | Custom Duplicate Check Condition Utility
Resolve remaining SQL Errors by referring to BTEQ Conversion Aid Workbook
| Copy Data into Tables using mirrored databases | Copy Table DAG
Execute Final BigQuery Script and ensure that the syntax is valid and the script doesn't execute without any issues
Composer DAG Development | Analyze the schedule dependencies and frequency of the jobs
Plan out scripts that will make up a branch in task group within each DAG instance
Create YAML Config Files to apply Templatized DAGs for all three activities: Ingestion (Inbound Files), Integration (Transformation & Sink) and Extraction (Outbound Files)
| Synch all source and config files to DAG Bucket through CICD Pipeline and generate the DAGs | CICD Pipeline
Dataflow Development | Apply Dataflow Templates for common scenarios (Read Data from Database / API and load into BigQuery Staging Tables)
Store connection and additional configuration in Secret Manager
Execute Templates using Dataflow Templated Job Start Operator within the DAG
Work with network team to resolve network and firewall issues
Test Data Setup & Testing | Create config files for copying data & back dating core tables for the date to be tested; Execute table Copy DAGs to load data into BigQuery | Copy Table DAG
Load additional tables not available in mirrored database separately
Ensure Latest Code is available in environment used for Testing in Dev Region; For QA, Source Code will be up to date through CICD Pipelines
Execute Application DAGS to test out scenarios
Execute Validation Scripts to ensure tests passed