## Sheet10
Item | PI Dashboard Remaining Activities | Environment / Global | Dependency | Owner | Ticket Required | Time Required
1 | Monitoring Project is created | Global |  | Platform Team | Yes | 1-3 Days (Wait)
2 | Logging Sink Dataset is created in Monitoring Project | Global | Item 1 | Platform Team | Yes | 1-3 Days (Wait)
3 | Create Broad Authorized Views for Airflow & BQ Logs on Monitoring Tables in auth_base_views dataset | Environment | Item 2 | Product Owner / Developer |  | 1-4 Hours (Review & Wait)
4 | Create Domain Level Dataset in all environment | Environment |  | Platform Team | Yes | 1-3 Days
5 | Add necessary authorizations (3 Authorizations per environment) | Environment | Item 2 and 4 | Product Owner |  | 30 Minutes
6 | Merge Monitoring & Audit Control Views changes to environment branches | Environment |  | Developer |  | 2 Hour
7 | Approval of GCP GITHUB Pull Request | Environment | Item 6 | LOB Lead / Onsite Lead & Product Owner |  | 1-4 Hours (Review & Wait)
8 | Create Operations and Cost Consumption Views in Domain Level dataset | Environment | Item 7 | Developer |  | 15 Minutes
9 | Modify Views in Operation_logs Dataset of EIM OPS (Consumer Project) | Environment | Item 8 | Joseph Van Hook |  | 1-2 Hours (Review & Wait)
10 | Insert records in Domain LOB Source System Mapping Table in Consumer Project | Environment |  | Developer |  | 1 Hour
11 | Fix Looker Dashboards to ensure filters reflect new LOB & ensure Visuals do not have LOB filter on Explore | Production Environment | Item 9 and 10 | Developer |  | 1 Hour
12 | Code Migration for Looker LookML Changes & Dashboard Corrections | Production Environment | Item 11 | BI Developer |  | 15 Minutes
13 | Approval of Looker GITHUB Pull Request | Production Environment | Item 12 | Joseph Van Hook / Robbie Vaughan |  | 15 Minutes