## Estimates
Area | Task | Count | Unit Estimate | Total Estimate | Task Details | Task Outcome | Estimate Comments
Github & Secret Manager Setup | Check Environment & Github Setup | 1 | 20 | 20 | • Check Services are executing • Check necessary access has been provisioned to required GCP Services and Github • Create necessary directories in Cloud Buckets • Create Composer connections and variables | Check list tracking each setup activity
| Create Secret Keys in Google Secret Manager | 3 | 5 | 15 | • Create Terraform Components (Core & Variables File) to define Google Secret Keys • Create GSM Workflow File • Coordinate with Github Admin to execute the Github Workflow on deployment Git branches | Secret Keys in Google Secret Manager | Based on no of Environments
| Testing the connectivity to Source Database & sFTP Server | 2 | 5 | 10 | • Create Source Config File • Test Connectivity using Connectivity DAG • Coordinate with Network Engineer if required for troubleshooting | Update Inventory Sheet to mark completion upon successful connectivity | Based on no of Connections
| BigQuery Dataset Creation Request & Authorization, Service Account Access to necessary Datasets | 1 | 5 | 5 | • Complete Mirroring Form • List authorization on source necessary datasetsfor other datasets • List Datasets for which Service Account needs to be authorize • Create Ticket for Mirroring Request | BigQuery Datasets are created. Necessary Authorizations are in place.
| General Configuration File for LOB | 3 | 5 | 15 | • Create Variables within YAML File for GCP Projects • Create Variables within YAML File for BigQuery Datasets • Create Variables within YAML File for Dataflow Settings • Create Variables within YAML File for Other Environment Information | YAML Script with necessary variables | Based on no of Environments
| Miscellaneous DAGs Setup | 1 | 20 | 20 | • Create DAG for Creating all Database Objects in each Dataset • Create DAG for Creating specific Database Objects • Create DAG for Copying Data • Create DAG for Adhoc SQL execution | Miscellaneous DAGs are created with successful execution.
| DB Object Creation - Tables and Views for LOB | 1 | 40 | 40 | • Configure Airflow Variable for Database Object Creation • Execute DAG for creating Database Object Creation | Tables and Views for the LOB
Ingestion | Source Configuration File | 31 | 2 | 62 | • Configure Variable with Source SQLs, Target Table, Schedule, DAG Dependency | Source Configuration File | Based on no of Staging Tables
| Ingestion DAG | 1 | 10 | 10 | • Create Dynamic DAG for Ingestion | Ingestion DAG
| Dataflow Template for Ingestion | 1 | 80 | 80 | • Create Dataflow Template for Ingestion | Dataflow Template for Ingestion
| Data Validation for Ingestion | 31 | 2 | 62 | • Execute Validation Scripts to compare counts between BigQuery & Teradata Tables • Troubleshoot Data Discrepancies between Teradata & BigQuery | Variability Report for Ingestion Tables | Based on no of Staging Tables
Integration | Pipeline Configuration File | 31 | 1 | 31 | • Configure Variable with List of SQL Scripts, Schedule, DAG Dependency | Pipeline Configuration File | Based on no of Core Tables
| Integration DAG | 1 | 10 | 10 | • Create Dynamic DAG for Integration | Integration DAG
| Data Validation for Ingestion | 31 | 3 | 93 | • Execute Validation Scripts to compare counts between BigQuery & Teradata Tables / Mirrored Views and verify data differences with mirrored views • Troubleshoot Data Discrepancies between Teradata & BigQuery • Document Cause of Variance between Teradata & BigQuery with example data | Variability Report for Core Tables | Based on no of Core Tables
Deployment & Other Activities | Alerting & Monitoring | 1 | 40 | 40 | • Create Terraform Scripts for Alerting & Monitoring • Execute DAG for creating Database Object Creation | Alerting Messages in Webex
| Code Deployment | 2 | 20 | 40 | • Create Pull Request for Code Deployment • Make sure necessary configurations are in place • Troubleshoot issues if they occur to ensure deployment is successful | DAGs running successfully in deployed environment | Based on no of Environments
| Dashboard Setup & Related Views | 1 | 10 | 10 | • Create \ Update views for monitoring and auditing in all three environments • Request for necessary authorizations for relevant datasets • Update Looker Code to ensure monitoring, costing and auditing data is available on the dashboards | Data available on the Looker Dashboards
Documentation | Operation Guide | 1 | 20 | 20 | • Document all DAGs created for the migration: Dag Purpose, Schedule, Target Tables, Prerequisites, Dependencies and Troubleshooting | Operation Guide
| Migration Plan | 2 | 20 | 40 | • List out all activities required for Code Deployment and Post Production Activities | Migration Plan
Total Development Estimate |  |  |  | 623
QA | Variance Analysis | 31 | 2 | 62 | • Analyze discrepancies between the Source and Target Table | Queries pointing variance or no variance | Based on no of Core Tables
| Table Level Documentation | 31 | 2 | 62 | • Document data validation for each table and point out discrepancies | Table Level Documentation | Based on no of Core Tables
| Variability Report Execution & Review | 1 | 10 | 10 | • Generate Variability Report for QA & Production Environments after deployment | Variability Report
Total QA Estimate |  |  |  | 134
Post Production Support / Hypercare |  |  |  | 40
Overall Estimates |  |  |  | 797

## Timelines
Month Indicator | Sprint | Activity to be completed | Responsibility | Tentative Start Date | Tentative End Date
Month 1 | Sprint 1 | BigQuery Table Setup & Ingestion | Eviden | 2024-12-09 | 2024-12-20
Month 1 | Sprint 2 | Integration | Eviden | 2024-12-23 | 2025-01-03
Month 2 | Sprint 3 (Half Sprint) with 1 Developer | Deployment + Hypercare | Eviden | 2025-01-06 | 2025-01-10
Formulas:
Tentative End Date = [Tentative Start Date]+11
Tentative Start Date = [Tentative End Date, row above]+3

## Resources
Role | Resources | # of Weeks | Total Hours | Billing Rate | Price | Cost to Company | CTC (USD) | Overal CTC (USD) | Margin | Margin with Set Price | Dollar Rate
Developers - Senior | 1 | 5 | 200 | 46.35 | 9270 | 2033.27 | 24.11 | 4822 |  |  | 84.34
Developers - Mid Level | 3 | 4 | 480 | 37.08 | 17798.4 | 1562.87 | 18.53 | 8894.4
QA Tester | 1 | 3 | 120 | 33.55 | 4026 | 1562.87 | 18.53 | 2223.6
All |  |  | 800 |  | 31094 |  |  | 15940 | 48.74% | 36.24%